## Sheet1
AR Office sensor demo, backlog
Index | Story | Deliverables | [6 empty] | Progress | Estimated Effort (hours) | Actual Effort (hours)
1 | Familiarize with Magic Leap | Can operate Magic Leap | [6 empty] | 20190218 - Started 20190218 - Done | 4 | 4
|  | Can build a sample app | [6 empty] | 20190218 - Started 20190219 - Testing 20190219 - Done | 4 | 2
|  | Can install and run sample app on device | [6 empty] | 20190218 - Started 20190219 - Testing 20190219 - Done | 4 | 2
|  | Can show a virtual object in real space | [6 empty] | 20190218 - Started 20190219 - Testing 20190219 - Done | 4 | 4
|  | Can use virtual object as button to change its color | [6 empty] | 20190219 - Started 20190220 - Skipped | 4
|  | Can interact with object | [6 empty] | 20190219 - Started 20190219 - Testing 20190220 - Done | 4 | 2
2 | App must know in which room it is. | Can scan the room. | [6 empty] | 20190219 - Started 20190219 - Testing 20190220 - Done | 8 | 2
|  | Can recognize the room after relaunch of app. | [6 empty] | 20190219 - Started 20190219 - Testing 20190220 - Done | 4 | 2
|  | Can place an object in the room and remember its location after relaunch. | [6 empty] | 20190219 - Started 20190219 - Testing 20190220 - Done | 4 | 2
3 | As a user I want to see sensor data in AR-space | Connect a Ruvi tag sensor to conNXT | [6 empty] | 20190221 - Started Using RaspberryPie to collect data from tags and connect to internet | 16
|  | Connect Magic Leap to conNXT | [6 empty] | To Do
|  | Show temperature (text) originating from sensor in AR-space | [6 empty] | To Do
4 | As a user I want to be able to register sensors | Register a 3d location in the room as a user. | [6 empty] | To Do
|  | Link this location to a sensor | [6 empty] | To Do
5 | As a user I want to see the temperature of a number of sensors in the room. | Draw (text) the temperature of a sensor 20 cm above the correct sensor | [6 empty] | To Do
6 | As a user I want to see a heatmap on the floor | Draw a filled circle of 1 meter radius around the sensor, but projected on the floor. | [6 empty] | To Do
|  | Give it a color corresponding to the temperature | [6 empty] | To Do
|  | Draw the actual temperature in the same color above the sensor. | 17°C | 19°C | 21°C | 22°C | 23°C | 24°C
7 | As a user I want to see the humidity in the room | Make a flipswitch to toggle between different kinds of information | [6 empty] | To Do
|  | Make it toggle between temperature and humidity data. | [6 empty] | To Do
|  | Show which data you are watching in text | [6 empty] | To Do
|  | Use this gradient to indicate the colors (but then fluent.) | [6 empty] | To Do
|  |  | 0% | 33% | 66% | 100%

## Inspiration
Heatmap football | https://www.google.nl/url?sa=i&source=images&cd=&cad=rja&uact=8&ved=2ahUKEwjN8qLXiMXgAhUP6qQKHZ7vA4sQjRx6BAgBEAU&url=https%3A%2F%2Frtsw.co.uk%2Fcategory%2Fnews%2F&psig=AOvVaw3D-fQoh0R7G_Hsn3UDRkxD&ust=1550571846015913
Heatmap kitchen | https://www.google.nl/url?sa=i&source=images&cd=&ved=2ahUKEwiV6KfniMXgAhXK1qQKHWiYDAQQjRx6BAgBEAU&url=https%3A%2F%2Fblogs.technet.microsoft.com%2Fmachinelearning%2F2016%2F12%2F16%2Fusing-cortana-intelligence-in-hololens-applications%2F&psig=AOvVaw3D-fQoh0R7G_Hsn3UDRkxD&ust=1550571846015913
AR heatmap | https://www.google.nl/url?sa=i&source=images&cd=&cad=rja&uact=8&ved=2ahUKEwiz19r8iMXgAhXRjqQKHR7YDqoQjRx6BAgBEAU&url=https%3A%2F%2Ftwitter.com%2Ffuturism%2Fstatus%2F730423493825802240&psig=AOvVaw3D-fQoh0R7G_Hsn3UDRkxD&ust=1550571846015913
wifi heatmap | https://www.google.nl/url?sa=i&source=images&cd=&cad=rja&uact=8&ved=2ahUKEwiqyYW0icXgAhVMr6QKHVceA7wQjRx6BAgBEAU&url=https%3A%2F%2Fwww.netspotapp.com%2Fbest-wifi-heatmap-software.html&psig=AOvVaw1bwujjYLFoADpz8VUsmles&ust=1550572105105583